Table of Contents

# Requirements Traceability Matrix — Governance Rollup

| Field | Value |
| --- | --- |
| Project | Ogma Library |
| Document | Traceability Matrix (governance rollup) |
| Owner | Chwezi Core Systems |
| Author | Peter Bamuhigire, Lead Consultant, Chwezi Core |
| Version | 2.0 |
| Date | 2026-07-06 |
| Status | Draft for owner sign-off |
| Standard basis | IEEE 1012-2016 (bidirectional traceability) |
| Classification | Confidential — Internal Use Only |

This is the governance-level rollup: business goals to requirement modules to verification method to implementation status. Per-requirement traceability detail (requirement → test case) lives in the SRS §8 (02-requirements-engineering/01-srs/08-verification-and-traceability.md); story-level traces live in 07-agile-artifacts/02-user-stories.md and _registry/baseline-trace.yaml. Counts agree with the closed FR inventory in _context/features.md (101 FRs) and statuses with _context/build-status.md (verified 2026-07-06).

## 1. Business Goals

- BG-001 Visible library — covers, shelves, metadata, multiple browsing modes.

- BG-002 Usable library — progress, bookmarks, annotations, search, statistics.

- BG-003 Intelligent library — an explainable AI advisor over the user's own collection.

- BG-004 Durable ownership — files stay the user's files; the catalogue augments, never replaces.

- BG-005 Private by default — on-device by default; every off-device transmission explicit, consented, reversible.

The classroom scope expansion (LAN/CLIENT/ADMIN, baseline v2.0) extends BG-001/BG-002 to a shared institutional collection and BG-005 to students as data subjects; no new business goal was created — the Change Impact Analysis entry for the expansion records this decision.

## 2. Forward Traceability: Goals → Modules → Verification → Status

| Business goal | FR module (count) | Primary verification method | Verification vehicle | Implementation status |
| --- | --- | --- | --- | --- |
| BG-001, BG-004 | LIB (7) | Test | Fixture-tree scanning and identity round-trip tests; golden corpus | 7/7 Done |
| BG-001, BG-002 | CAT (7) | Test | View-equivalence and filter-conjunction assertions; smart-shelf evaluator tests | 6/7 Done; FR-CAT-007 Planned |
| BG-001, BG-004 | META (8) | Test | Provider-stub lookups; write-back fault injection; health-dashboard checks | 8/8 Done |
| BG-002, BG-004 | READ (15) | Test | Reader-state round-trip; annotation durability; OCR and password fixtures | 14/15 Done; FR-READ-012 Planned |
| BG-002, BG-003 | SEARCH (6) | Test | Query-replay benchmarks; index rebuild reconciliation | 6/6 Done |
| BG-003, BG-005 | AI (11) | Test | Gateway payload-capture and tier-enforcement tests; AI evaluation harness | 10/11 Done; FR-AI-008 Planned |
| BG-001, BG-005 (institutional) | LAN (10) | Test | Phase 16 LAN verification tooling; path-validation and TLS/TOFU tests | 10/10 Done (Windows-verified; macOS/Linux pass open, retro action A-5) |
| BG-002, BG-005 (students) | CLIENT (13) | Test | Sync-conflict, offline-cache, profile-isolation, read-only architecture tests | 13/13 Done |
| BG-003, BG-005 (students) | ADMIN (13) | Test | Proxy key-capture, quota-enforcement, audit-export tests; DPIA screening | 13/13 Done |
| BG-004 (ecosystem) | EXT (3) | Test (planned) | Gateway-enforced plugin contract demonstration; import reconciliation | 0/3 — Planned (Phase 23) |
| BG-001, BG-002 | UX (8) | Test + Inspection | Headless UI state tests; scripted journeys on W-REF-01; WCAG 2.2 AA audit | 2/8 Done; 4 In verification (Phases 20–21); FR-UX-003, FR-UX-006 Planned |
| Total | 101 | — | — | 89 Done, 4 In verification, 8 Planned |

## 3. Backward Traceability: Coverage of Each Goal

Every business goal has implementing requirements and no goal is orphaned:

| Business goal | Implementing modules | Delivered evidence today |
| --- | --- | --- |
| BG-001 | LIB, CAT, META, LAN, UX | Catalogue, 4 views incl. 3D shelf, health dashboard, published host catalogues |
| BG-002 | READ, SEARCH, CAT, CLIENT, UX | Resume/annotations/search shipped; formal journey measurement pending Phase 20 |
| BG-003 | AI, SEARCH, ADMIN | Explained recommendations, plans, semantic search, managed classroom AI; answer mode pending |
| BG-004 | LIB, META, READ, EXT | Identity preservation, reversible write-back, citation export; importers/read API pending |
| BG-005 | AI, LAN, CLIENT, ADMIN + CTRL-001..024 | Tier system, payload preview, Privacy Center, student privacy isolation; at-rest encryption pending Phase 19 |

Conversely, every FR module names its goals (column 1 of §2), so no implemented capability lacks a business anchor.

## 4. NFR → Mechanism → Test Layer

| NFR | Budget/obligation | Implementing mechanism | Test layer / evidence | Status |
| --- | --- | --- | --- | --- |
| NFR-OGMA-001 | Cold start ≤ 3 s (P95, W-REF-01) | Deferred service start, skeleton shell | CI benchmark (trend) → Phase 20 acceptance | Trend-only |
| NFR-OGMA-002 | Catalogue load ≤ 2 s, 2,000 books | Read-model projection, virtualised views | gc-perf-2000 corpus benchmark → Phase 20 | Trend-only |
| NFR-OGMA-003 | Metadata search ≤ 150 ms | In-memory read model + indexed queries | Query-replay benchmark → Phase 20 | Trend-only |
| NFR-OGMA-004 | Full-text search ≤ 500 ms warm | FTS5 external-content index, BM25 | Query-replay benchmark → Phase 20 | Trend-only |
| NFR-OGMA-005 | Page turn ≤ 100 ms cached | PageRenderCache | Render-cache benchmark → Phase 20 | Trend-only |
| NFR-OGMA-006 | 3D shelf ≥ 60 FPS, 500 books | Virtualised Three.js scene, spine texture atlas | WebView frame timing on UHD 620 → Phase 20 | Trend-only |
| NFR-OGMA-007 | AI gateway overhead ≤ 10 s metadata-only | Gateway instrumentation timestamps | Gateway-side elapsed minus provider round-trip | Trend-only |
| NFR-OGMA-008 | Annotation durability | Transactional annotation persistence | Fault-injection round-trip tests | Passing (dev evidence) |
| NFR-OGMA-009 | Job recovery, no duplicate work | Idempotent background workers, job journal | Kill-and-restart fault injection | Passing (dev evidence) |
| NFR-PROD-001 | Local-first availability/offline | On-device catalogue, sidecar, local AI path | Network-blocked integration tests | Passing (dev evidence) |
| NFR-PROD-007/008 | WCAG 2.2 AA keyboard/screen-reader | Icon + aria label per control, keyboard paths | Headless UI walkthroughs → Phase 21 audit | In verification |
| NFR-PROD-009 | Data portability, no lock-in | Portable export bundle (catalogue + sidecar) | Export/import round-trip test | Passing (dev evidence) |
| NFR-PROD-010 | Reversible destructive operations | Backup → diff → verify → restore pipeline | Write-back fault injection | Passing (dev evidence) |
| NFR-PROD-011 | Signed builds, idempotent backed-up migrations | EF migrations (10, idempotent); signing at Phase 22 | Migration tests; packaging pending | Partial — signing Planned |
| NFR-PROD-013/014 | Audit trail; AI history/embedding erasure | AuditEvents, scoped erasure services | Erasure-residue and audit tests | Passing (dev evidence) |

Rule of interpretation (from _context/reference-hardware.md): NFR-OGMA budgets are binding for release gates at MVP scale; all pre-Phase-20 measurements are trend-only and never asserted as acceptance evidence. Where an NFR-PROD default and an NFR-OGMA budget address the same attribute, NFR-OGMA binds at 2,000-book scale and NFR-PROD holds as the 50,000-item V1 target gated at Phase 20.

## 5. Gap Analysis

| # | Gap | Severity | Remediation |
| --- | --- | --- | --- |
| G-1 | 8 Planned FRs have no implementing code (FR-CAT-007, FR-READ-012, FR-AI-008, FR-EXT-001..003, FR-UX-003, FR-UX-006) | Major (release-scope) | Scheduled in the forward sprint plan, Sprints 2–6; not release blockers for the personal MVP except FR-UX-006 (owner decision pending) |
| G-2 | All NFR-OGMA performance figures are trend-only | Major | Phase 20 acceptance on W-REF-01/M-REF-01 (story US-053) |
| G-3 | LAN/CLIENT verification recorded on Windows only | Minor | macOS/Linux verification pass, retrospective action A-5, due 2026-08-07 |
| G-4 | _registry/baseline-trace.yaml still traces the v1.0 story set (US-001..020) | Major (governance) | Registry re-sync to US-001..US-059, retrospective action A-7, due 2026-07-17 |
| G-5 | SRS §8 traceability table predates the LAN/CLIENT/ADMIN/EXT/UX modules | Major (documentation) | SRS §8 refresh is owned by the requirements workstream; this rollup carries the v2.0 truth meanwhile |

No orphan requirement exists (every FR appears in §2 with a goal and a story); no orphan goal exists (§3). Coverage: 101/101 FRs traced to goals and stories (100%); test-evidence coverage 93/101 (89 Done + 4 In verification implemented with tests), 92.1%.

## 6. Revision History

| Version | Date | Change |
| --- | --- | --- |
| 2.0 | 2026-07-06 | First governance rollup at baseline v2.0; replaces group-only traceability noted as a v1.0 defect in ../audit-report.md |