# Deployment and Operations

Table of Contents

# 1	Deployment and Operations

## 1.1	Ogma Library

| Field | Value |
| --- | --- |
| Document | Deployment and Operations |
| Owner | Chwezi Core Systems |
| Author | Peter Bamuhigire, Lead Consultant, Chwezi Core |
| Version | 2.0 |
| Status | Draft for owner sign-off |
| Date | 2026-07-06 |
| Classification | Confidential — Internal Use Only |

## 1.2	Scope Note

Ogma Library is a local-first desktop application for Windows and macOS with an opt-in LAN host mode for classrooms. It is not a hosted multi-tenant service. This document therefore covers the operations a desktop product actually owns: release engineering across the Dev, Alpha, Beta, and Stable channels (ADR-0009); the signed auto-update trust chain; the build/sign/notarize pipeline; opt-in, local-first telemetry; the release-hosting and code-signing supply chain; security incident response for signing keys and the update feed; and — new in version 2.0 — the operational runbook for a school running the LAN host.

## 1.3	Honesty Baseline (read before any checklist in this phase)

Version 2.0 exists to correct a defect in v1.0: the v1.0 go-live checklist was presented pre-checked, asserting that gates, rollback drills, signing, and telemetry verification had all passed when none of that infrastructure exists. That was fiction and it is withdrawn. In version 2.0:

- Every checklist item is unchecked unless _context/build-status.md or a named repository artifact proves it, and each open item names an owner, an evidence pointer, and a target phase.

- Distribution, packaging, signing, the release host, and the telemetry sink are designed here but not built — the repository contains no packaging configuration (Phase 22 scope) and no telemetry sink (Phase 23 scope). Sections describing them are written as executable plans and are explicitly marked Planned.

- What does exist and is verifiable today: the application itself (Phases 00–18 implemented), 800 executed automated cases with 0 failures in the 2026-08-13 canonical Release run (see ../05-testing-documentation/test-completion-report.md), the CI pipeline on Windows + macOS, and the governance documents this phase mirrors.

This document is the intellectual property of Chwezi Core Systems. No part may be reproduced or disclosed without written permission.

\newpage

# 2	Release and Update Infrastructure

Ogma Library runs on the user's device; the only remote infrastructure the product owns is the release-hosting and code-signing supply chain plus an opt-in crash-report sink. No user library content, catalogue data, or reading state is ever stored on an Ogma Library server. This section inventories that infrastructure with an explicit status per component — most of it is planned, not provisioned.

## 2.1	1. Infrastructure Inventory with Status (2026-07-06)

| Component | Purpose | Custody owner | Status |
| --- | --- | --- | --- |
| GitHub repository + Actions CI | Source of record; per-PR restore/format/build/test on windows-latest + macos-latest (.github/workflows/ci.yml) | Chwezi Core Systems | Exists |
| Commit-message hook + branch protection | Conventional Commits enforcement (.github/hooks/commit-msg); merge rules per docs/governance/BRANCH-STRATEGY.md | Chwezi Core Systems | Exists (hook); branch-protection settings to be confirmed at Phase 22 |
| Static release host / CDN | Serves Velopack descriptors, full/delta packages, DMG, MSIX | Chwezi Core Systems | Planned — Phase 22 |
| Velopack channel feeds (Dev/Alpha/Beta/Stable) | Per-channel signed update descriptors | Chwezi Core Systems | Planned — Phase 22 |
| GitHub Releases | Public installers of record with checksums | Chwezi Core Systems | Planned — Phase 22 |
| Code-signing key custody (Authenticode + Apple Developer ID) | Signing material in an HSM or platform secure store; never plaintext on a runner | Chwezi Core Systems | Planned — Phase 22 (no certificates provisioned) |
| Apple notarization + Mac App Store account | Notarize DMG; MAS distribution | Apple, under Chwezi Core Systems account | Planned — Phase 22 (account enrollment outstanding) |
| Microsoft Partner Center / Store listing | MSIX Store + enterprise channel | Microsoft, under Chwezi Core Systems account | Planned — Phase 22 |
| Crash-report sink | Receives opt-in crash reports and minimal counters | Chwezi Core Systems | Planned — Phase 23 (no sink; app transmits nothing) |

## 2.2	2. Update Trust Chain (design ratified; verification lands at Phase 22)

Per ADR-0009 and CTRL-OGMA-012/013:

- CI signs each Windows build (Authenticode) and signs + notarizes each macOS build (Developer ID), requesting signing operations from the key-custody service over an authenticated session — key material never leaves the store, and every signing operation is logged with the requesting build identifier.

- The Velopack feed descriptor is itself signed, so descriptor verification is independent of transport.

- The installed application verifies descriptor signature, then package signature, before applying an update; a failure discards the package and writes a local AuditEvents record.

- Signing material rotates on a fixed schedule and immediately on suspected compromise (runbook: signing-certificate expiry; malicious-update entry).

## 2.3	3. Crash-Report Sink Design (Planned — Phase 23)

Accepts data only from users who enabled opt-in telemetry. Payload minimized at source: anonymous install identifier, application version, OS version, exception type + stack signature, aggregate counters. Never: library content, file paths or names, catalogue metadata, search queries, AI history. The same payload-preview and privacy-tier rules that govern AI egress govern this surface. The default-off behaviour is verifiable today by construction — no telemetry code exists — and will be re-verified by an explicit default-off egress test when the surface is built.

## 2.4	4. Classroom/LAN Infrastructure (school-owned, product-supported)

The LAN host is implemented in the product (Phase 16–18 code: KestrelHostModeListener, mDNS advertisement, TLS provisioning, trust store) and runs on school-owned hardware — it is the school's infrastructure, operated with the LAN-host runbook in runbook.md. Chwezi Core Systems hosts nothing for a school; the school's AI keys live in the host machine's OS credential store (FR-ADMIN-004) and its audit log is local and exportable (FR-LAN-010).

## 2.5	5. Incident-Response Flow

The detect → triage → contain → eradicate → recover → review flow below is authoritative for the two highest-severity infrastructure incidents — signing-key compromise and a malicious-update report. Per-incident operational steps live in runbook.md. The flow is a written procedure; the first tabletop rehearsal is a Phase 23 exit criterion (go-live register Section 4).

flowchart TD
    A[Detect] --> B[Triage]
    B --> C[Contain]
    C --> D[Eradicate]
    D --> E[Recover]
    E --> F[Review]

    A -->|Sources: crash-report sink anomaly,\nmalicious-update report,\nkey-store access alert| B
    B -->|Classify severity,\nassign incident owner| C
    C -->|Pull the affected feed descriptor,\nsuspend publishing,\nrevoke or freeze signing key| D
    D -->|Rotate signing material,\nrebuild from a clean runner,\nremove the bad package| E
    E -->|Publish a signed corrective release,\nverify update success,\nrestore the channel| F
    F -->|Post-incident review,\nupdate this flow and the runbook,\nrecord lessons| G[Closed]

The flow is reviewed after every invocation and at each release-gate sign-off so the diagram and runbook stay consistent with the live infrastructure.

\newpage

# 3	Release, Build, Sign, and Distribute Guide

Implementation status: PLANNED. This guide is the executable plan for Phase 22 ("Packaging, Signing & Store Submission", docs/plans/grand-plan/phase-22/README.md, status: not started). The distribution design is ratified — ADR-0009 (docs/adrs/0009-velopack-msix-dmg.md, ratified 2026-05-30) — and Velopack 1.0.1 was proven to restore/build on net10.0 in spike S1. No packaging configuration exists in the repository today: no vpk invocation, no MSIX manifest, no notarization profile, no release workflow beyond CI build-and-test. Every command below is the plan to be executed and verified at Phase 22, not a record of something that has run.

## 3.1	1. Distribution Targets (ADR-0009)

One pipeline produces four coordinated distribution targets:

| Target | Format | Channel role | Tier (Phase 22 plan) |
| --- | --- | --- | --- |
| Velopack direct feed | Full + delta packages per channel (Dev/Alpha/Beta/Stable), Windows and macOS | Team-controlled auto-update path; signature-verified descriptor and packages | MVP |
| GitHub Releases | Velopack full installers + checksums attached to tagged releases | Public download of record; beta distribution alongside the Beta feed | MVP |
| Microsoft Store | MSIX (Authenticode-signed) | Store discovery and enterprise policy deployment on Windows | V1 |
| Mac App Store + direct DMG | Notarized, Developer ID-signed DMG for direct; MAS build for the store | macOS distribution meeting Gatekeeper expectations | V1 (DMG) / Final (MAS) |

## 3.2	2. Channel Model

Four Velopack feed paths separate stability tiers. A build is promoted, never rebuilt — promotion re-points the next channel's feed at the already-signed artifact, which is why Deterministic=true builds and signed packages matter:

- Dev — every merge to develop publishes a Dev build (continuous, no change window).

- Alpha — promotion of a Dev build that passed smoke verification on Windows and macOS.

- Beta — promotion of an Alpha build after every release gate G1–G8 passes formally (Test Strategy Section 7 — none has passed formally yet).

- Stable — promotion of a Beta build that completed its soak window (≥ 2 weeks, Phase 23 plan) without a blocking defect.

## 3.3	3. Planned Pipeline (to be implemented and drilled at Phase 22)

Steps 1–10 constitute the release procedure; each acquires its verification evidence at Phase 22 before first use.

- Tag the release commit on release/<semver>: git tag -s v<semver> (signed tag; main merge rules per docs/governance/BRANCH-STRATEGY.md). The tag is the single release coordinate on every artifact and gate record.

- CI builds Release configuration from the tag on both runners: dotnet publish src/OgmaLibrary.App -c Release -r win-x64 and -r osx-arm64 (plus osx-x64 if the owner ratifies Intel-mac support; open decision for Phase 22).

- Run the full verification suite; a channel release proceeds only when the gates applicable to that channel pass and the run is recorded.

- Windows signing: sign the published binaries with Authenticode via the key-custody service (Section 4 of infrastructure.md); key material never lands on the runner disk.

- Velopack packaging (both platforms): vpk pack --packId OgmaLibrary --packVersion <semver> --packDir <publish-dir> --channel <channel> producing full + delta packages and the feed descriptor; then vpk upload (or an equivalent copy step) to the channel's feed path on the release host. Exact vpk argument set is fixed when Phase 22 lands the tooling version.

- macOS: sign with Developer ID (codesign --deep --options runtime), notarize (xcrun notarytool submit <artifact> --wait), staple (xcrun stapler staple), then produce the DMG.

- MSIX (Stable only): produce the MSIX from the publish output with a manifest to be authored in Phase 22 (Package.appxmanifest), sign, validate with the Windows App Certification Kit, submit via Partner Center.

- Sign the Velopack feed descriptor itself so descriptor verification is independent of transport (CTRL-OGMA-012/013).

- Publish: feed paths for the channel + GitHub Release with checksums.

- Record the release in the release log: version, channel, commit, signing identifiers, gate-run references.

## 3.4	4. Update Trust Chain (design; verification oracles land with Phase 22 tests)

- The installed application fetches the channel descriptor over an integrity-checked connection.

- It verifies the descriptor signature, then the package signature, before applying anything.

- A package failing either check is discarded and the failure is recorded in the local AuditEvents table.

- Phase 22 test oracle: a deliberately tampered descriptor and a tampered package must both be rejected on both platforms (Test Strategy Section 9.4).

## 3.5	5. Change Window and Freeze Policy (policy — effective from first Beta)

- Routine Beta/Stable releases publish Tuesday or Thursday, 09:00–13:00 East Africa Time, at the start of the window so the release owner watches the update-success signal for the remainder.

- Code freeze begins 24 hours before a scheduled Stable window; only release-blocking fixes merge during freeze.

- Beta/Stable testers receive a release notice ≥ 24 hours ahead: version, headline changes, and whether a database migration is included.

- Emergency security releases may publish out-of-window through the full pipeline, with the justification recorded in the release log.

## 3.6	6. Database Migration Safety (implemented in-app; release procedure planned)

The application side exists and is tested: migrations apply transactionally with a backup-before-apply snapshot of the catalogue of record, verified by Catalogue/MigrationTests.cs across the 10 EF Core migrations (latest Phase18SchoolAdminTables). The release-side rules:

- A release that includes a migration says so in its release notice.

- The pre-migration backup is retained until the migrated version has launched successfully at least once, so a downgrade path exists.

## 3.7	7. Rollback Procedure (planned; drilled against a staging feed before first Beta — a go-live blocker)

- Detect the regression (update-success signal, crash signal, or user report); open an incident per runbook.md.

- Freeze publishing on the affected channel.

- Re-point the channel feed descriptor at the previous known-good signed release. The previous 2 Stable releases' full packages and descriptors are always retained for exactly this purpose.

- Publish the previous version as current so auto-update pulls the older build forward.

- If the defective update migrated the database, the release notice and in-app message direct users to the backup-restore steps in the runbook's corrupted-database entry before downgrading.

- Confirm recovery via the update-success and crash-free signals; record the rollback and feed the cause into the post-incident review.

Status: this procedure has never been executed. The go-live readiness register carries "rollback drill executed against a staging feed" as an unchecked blocker with owner and target phase (Phase 22).

\newpage

# 4	Telemetry and Service Levels

Implementation status: definitions binding now; measurement surface Planned — Phase 23. Ogma Library currently transmits no telemetry of any kind because no telemetry code exists. When the opt-in surface is built (Phase 23), these definitions govern it; until then the SLO table is a commitment, not a measurement.

## 4.1	1. Telemetry Model — Opt-In, Local-First

- Telemetry is opt-in; the default state collects and transmits nothing off-device. The product is fully functional with telemetry off, forever.

- Payload is minimized at source: anonymous install identifier, application version, OS version, exception type + stack signature, aggregate event counters. Never library content, file paths/names, catalogue metadata, search queries, or AI history.

- The user can inspect what would be sent (the same payload-preview pattern the AI gateway uses), disable at any time, and request erasure of previously sent reports (NFR-PROD-014 pattern applied to telemetry).

- Local health signals (job failures, crash markers, audit events in AuditEvents) remain on-device regardless of the telemetry setting; the LAN-host audit log is local to the school.

## 4.2	2. Definitions

- SLI — a measured quantity describing one aspect of service health.

- SLO — the target an SLI must meet over a stated window. All objectives here are internal SLOs over a rolling 30-day window; Ogma Library makes no contractual SLA to end users. The single provider-side SLA is the release host/CDN's own commitment, tracked under its contract.

- Error budget — the share of events permitted to miss the objective in the window; exhaustion freezes non-essential releases on the affected channel and triggers runbook escalation.

## 4.3	3. Service-Level Objectives (binding from first public Beta)

| SLI | Definition | SLO | Error budget |
| --- | --- | --- | --- |
| Update-success rate | Successful update applications ÷ update attempts reported by consenting clients; success = signature verification passes and the new version launches once | ≥ 99.0% | 1.0% of attempts |
| Crash-free session rate | Sessions ending without an unhandled-exception termination ÷ total sessions from consenting clients | ≥ 99.5% | 0.5% of sessions |
| Release-host availability | Successful feed/package responses ÷ total requests (synthetic probes + consenting-client outcomes) | ≥ 99.9% (≈ 43 min/30 days) | 0.1% of requests |
| Median update download time | Median wall-clock time to download a delta package, normalized to a reference 25 Mbps connection | ≤ 8 s at the median | Binds at the median; the slower half is not budgeted |

Notes per indicator:

- A signature-verification failure counts against update-success and raises the malicious-update runbook path — it is never just a statistic.

- Crash-free 99.5% is the productivity-domain target behind NFR-PROD-006; it is unmeasurable until the Phase 23 opt-in surface exists, which is exactly why NFR-PROD-006 carries "no evidence possible today" in the test strategy.

- Median download time isolates delta-packaging regressions from user link speed; a breach is investigated in the packaging pipeline, not blamed on networks.

## 4.4	4. Classroom/LAN Host Signals (school-local, never transmitted)

The LAN host exposes operational signals to the school administrator only, on the host machine: active session count and per-session activity (FR-LAN-007), host audit log of connections/streams/denials (FR-LAN-010), AI usage/cost/quota utilization per class and student (FR-ADMIN-010). These are dashboards over local data (SchoolUsageDashboardServiceTests verifies the figures), not telemetry — nothing leaves the school.

## 4.5	5. Reporting and Review

- The four SLIs are reviewed at each release-gate sign-off and at each 30-day window close, from first Beta onward.

- A window with an exhausted budget is recorded; cause analysed in the post-incident review; corrective action tracked to closure before the next Stable change window.

- SLO instrumentation itself is a go-live blocker: the readiness register carries it unchecked with owner and Phase 23 target until the measurement surface exists and has produced its first honest window.

\newpage

# 5	Operational Runbook

This runbook gives a responder a deterministic procedure per incident. Two operating contexts exist: release operations (Chwezi Core Systems' own supply chain — feeds, signing, telemetry) and, new in version 2.0, LAN-host operations (a school running the classroom host on its own hardware). Release-operations entries that depend on the update feed or telemetry are executable only once Phase 22–23 infrastructure exists; they are the procedures that will be drilled at Phase 23. The LAN-host entries are executable today because the host features are implemented (Phases 16–18).

## 5.1	1. Incident Severity

| Severity | Definition | Initial response time |
| --- | --- | --- |
| SEV-1 | Signing-key compromise; malicious-update report; an update that crashes on launch for a population; school AI key exposure | 15 minutes |
| SEV-2 | Crash spike above error budget; failed-update rate breaching its SLO on a live channel; LAN host serving unpublished content | 1 hour |
| SEV-3 | Single user's corrupted database; non-blocking update failure; single classroom client fault | 1 business day |

## 5.2	2. Release Operations

### 5.2.1	2.1 Failed Update (executable from first Beta)

- Classify: signature-verification rejection, download failure, or post-install launch failure (crash-sink signatures + release-host logs).

- Signature rejection of a legitimate package → treat as SEV-1 and jump to 2.4 (a verification failure may indicate a tampered feed).

- Post-install launch failure → freeze the channel, execute the rollback procedure (deployment guide Section 7).

- Release host failing to serve → escalate to the CDN provider under its agreement.

- Confirm recovery: update-success SLI returns above 99.0%.

### 5.2.2	2.2 Corrupted Local Database (executable today — procedure is app-level)

- User closes the application so no process holds the database file.

- Restore the most recent timestamped backup of the catalogue of record and sidecar index (created by the backup-before-apply rule; the mechanism is tested by Catalogue/MigrationTests.cs).

- No backup → rebuild derived state: re-scan the library root (files remain the user's files, FR-LIB principles) and rebuild the search index from source (IndexManagerService rebuild path, FR-SEARCH-006). User-authored data inside the database cannot be rebuilt — which is why the backup rule exists.

- If corruption followed an update, escalate to 2.1 and consider a channel rollback.

### 5.2.3	2.3 Crash Spike (executable from first Beta; needs telemetry)

- Declare SEV-2; assign an incident owner.

- Group crash signatures; correlate the dominant fault with the latest release on the channel.

- Release-correlated → freeze channel, roll back. Environment-specific → targeted fix at the next change window.

- Confirm: crash-free SLI back above 99.5%.

### 5.2.4	2.4 Malicious-Update Report / Signing-Key Compromise (SEV-1)

Follow the incident-response flow in infrastructure.md Section 5:

- Contain: suspend publishing; pull the affected feed descriptor; freeze or revoke the signing key.

- Eradicate: rotate signing material; rebuild from a clean runner; remove the bad package.

- Recover: publish a signed corrective release; re-point the channel; verify update-success recovery.

- Review: post-incident review; update this runbook and the flow diagram.

First tabletop rehearsal of this entry is a Phase 23 exit criterion — it has not been drilled.

### 5.2.5	2.5 Signing-Certificate Expiry

- Renewal is scheduled ≥ 30 days ahead of expiry (monitored alert once key custody exists, Phase 22).

- Install the renewed certificate into the key store; re-run a Dev build to confirm signing and notarization.

- Already expired with releases blocked → SEV-1; escalate per Section 4.

## 5.3	3. LAN-Host Operations (school administrator; executable today)

These procedures operate the implemented classroom host. The admin surfaces referenced are the host-sharing panel (HostSharingViewModel in OgmaLibrary.App) and the school-admin dashboard; behaviours cited are covered by the tests named in the deterministic-check catalogue (DC-LAN, DC-ADMIN).

### 5.3.1	3.1 Enable / Disable Host Mode

- Enable: open the sharing panel → start hosting → confirm the explicit start-confirmation prompt (host mode is opt-in and audited, FR-LAN-001). Verify: clients can discover the host (mDNS) or join by address; the join code/QR displays; the audit log records the start event.

- Disable: stop hosting from the same panel. Verify: the listener stops (no inbound port); connected clients degrade gracefully to their local libraries (FR-LAN-008, FR-CLIENT-011) and re-sync on the next start.

- Publishing scope check after any enable: only admin-published folders/shelves are enumerable (FR-LAN-009). If unpublished content is reachable, treat as SEV-2, disable host mode immediately, and export the audit log before investigating.

### 5.3.2	3.2 TLS Certificate Rotation (host)

- Rotate the host certificate from the sharing panel (provisioning is automatic — LanHostCertificateProvisioner).

- Expect every client to see a fingerprint change on next connection: trust-on-first-use means clients must refuse the new fingerprint until re-trusted (FR-LAN-004; HostTrustServiceTests verifies refusal).

- Communicate the new fingerprint to the class through an out-of-band channel (displayed on the host screen); students re-trust after comparing fingerprints.

- Rotate immediately (not on schedule) if the host machine was compromised or the certificate's private key may have leaked; then also revoke all sessions (3.3).

### 5.3.3	3.3 Session and Enrollment Revocation

- Revoke a session: sharing panel → sessions list → revoke. The revoked session's next request is rejected; other sessions are unaffected (FR-LAN-007).

- Revoke an enrollment (student/teacher profile): admin panel → profiles → revoke. Takes effect at next connection; the student keeps local notes but loses host access (FR-CLIENT-009).

- After any suspected credential sharing: revoke the affected profile, re-issue a join code, and export the host audit log (FR-LAN-010) for the period in question.

### 5.3.4	3.4 School AI Key Rotation / Exposure (SEV-1 if exposed)

- The school AI key lives only in the host machine's OS credential store and is never transmitted to clients (FR-ADMIN-004; AiProxyEndpointHandlerTests asserts no key bytes in client payloads).

- Routine rotation: admin panel → school AI settings → delete the stored key → save the new key → run the key test action. Verify a student query succeeds through the host gateway afterward.

- Exposure response: revoke the key at the AI provider first, then rotate in-app; review the AI usage dashboard (FR-ADMIN-010) for anomalous spend during the exposure window; purge institution AI history if student queries may have been exfiltrated (FR-ADMIN-013).

- Quota sanity check after rotation: per-student and per-class quotas and rate limits still enforce (FR-ADMIN-008/009).

### 5.3.5	3.5 Host Machine Failure

- Clients continue reading from offline caches and local state — nothing is lost by design (FR-LAN-008, FR-CLIENT-005/011).

- Restore the host: reinstall Ogma Library, restore the host catalogue from the school's backup of the library folder + catalogue database, re-enable host mode, re-provision the certificate (clients re-trust per 3.2).

- Client reading state re-syncs on reconnect with per-field latest-writer-wins and no silent loss (FR-CLIENT-006).

## 5.4	4. Escalation Path

| Tier | Role | Owner | Engaged when |
| --- | --- | --- | --- |
| Tier 1 | Release on-call | Peter Bamuhigire | First responder, every release-ops incident |
| Tier 2 | Release owner | Peter Bamuhigire | SEV-1 at declaration; any missed response-time target |
| Tier 3 | Chwezi Core Systems incident lead | Chwezi Core Systems | Signing-key compromise / malicious update; SEV-1 not contained in 1 hour |
| School tier | School administrator | Named per school | All Section 3 incidents; escalates to Chwezi Core support only for product defects |
| External | CDN provider, Microsoft Store, Apple | Respective provider | Host outage, Store takedown, notarization failure |

- SEV-1 escalates to Tiers 2 and 3 at declaration, in parallel.

- Tier 1 records the timeline, actions, and outcome in the release log and opens the post-incident review; a school administrator records LAN incidents in the exported host audit log.

- Single-operator caveat, stated plainly: Tiers 1 and 2 are the same person today. That is acceptable for a pre-beta product and is a staffing risk to revisit at the Phase 23 launch decision; the register carries no pretence of a 24/7 rota.

\newpage

# 6	Public-Beta Go-Live Readiness Register

This register is the go/no-go gate for opening the public Beta channel. Version 2.0 replaces the v1.0 checklist, which was published pre-checked — asserting passed gates, executed rollback drills, verified signing, and instrumented SLOs when none of that infrastructure exists. That presentation was fictional and is withdrawn. The rule in force now:

An item is checked only when a named evidence artifact proves it. Every unchecked item carries an owner, an evidence pointer (what will prove it), and a target phase. Current truth source: _context/build-status.md and commit 26df98322b7934919ddaba513ac02d9aaa44edbb, verified 2026-08-13.

Overall recommendation as of 2026-08-13: NO-GO for public beta or production. The repository has broad code/test evidence, but explicit capability stubs and the Phase 19–23 security, performance, accessibility, packaging, operational, legal, design, and commercial gates remain open.

## 6.1	1. Release-Gate Readiness (G1–G8)

Status vocabulary: automated oracle green = the gate's pass oracle runs and passes in the test suite today; formal acceptance = a recorded gate run on reference hardware or against a release-candidate build, which is what "passed" means. Detail per gate: Test Strategy Section 7.

- G1 — WebView bridge on both platforms. Spike S3 passed 7/7 headless contract checks and Shelf3D/BridgeMessageTests.cs is green, but the live WebView2/WKWebView round-trip is deferred (TRACK-P01-S3-WEBVIEW-RUNTIME). Owner: Peter Bamuhigire. Evidence: E2E run record on real WebViews. Target: Phase 21.

- G2 — PDF render + password open on target platforms. PDFtoImage selected via spike S2 (dev-trend P95 124–157 ms); PdfiumAdapterPasswordTests green. No reference-hardware render benchmark. Owner: Peter Bamuhigire. Evidence: Phase 20 benchmark file in docs/benchmarks/phase-20/. Target: Phase 20.

- G3 — 500-book responsiveness on W-REF-01. No reference-hardware run of any kind exists. Owner: Peter Bamuhigire. Evidence: recorded W-REF-01 benchmark. Target: Phase 20.

- G4 — 2,000-book responsiveness on W-REF-01. Spike S5 gives FTS trend only (P95 1.97 ms, dev box). Owner: Peter Bamuhigire. Evidence: recorded W-REF-01 benchmark over gc-perf-2000. Target: Phase 20.

- G5 — Write-back backup/restore. Automated oracle green (Metadata/PdfWriteBackTests.cs). Formal run against a release-candidate build not recorded. Owner: Peter Bamuhigire. Evidence: gate entry in docs/qa/BETA-GATES-STATUS.md. Target: Phase 22.

- G6 — AI privacy payload preview. Automated oracle green (PayloadPreviewViewModelTests, AiGatewayTests, classroom path AiProxyEndpointHandlerTests). Phase 19 security re-verification with SAST + threat model outstanding. Owner: Peter Bamuhigire. Target: Phase 19.

- G7 — Index rebuild from scratch. Automated oracle green (IndexManagerServiceTests). Formal recorded run outstanding. Owner: Peter Bamuhigire. Target: Phase 22.

- G8 — Interrupted-job recovery. Automated oracle green (JobManagementTests, OcrJobQueueServiceTests). Formal recorded run outstanding. Owner: Peter Bamuhigire. Target: Phase 22.

Summary: 8 gates open. G5–G8 are close (oracle automated and green; needs a recorded release-candidate run). G1–G4 need platform/hardware work that has not begun.

## 6.2	2. Build and Test Health (prerequisite to everything above)

- Canonical Release test green at the inspected commit. dotnet test OgmaLibrary.sln -c Release --nologo -v minimal passed 800/800 cases on 2026-08-13. Evidence: ../05-testing-documentation/test-completion-report.md. This is code-level evidence, not a packaged-release approval.

- Dependency vulnerability audit green at the inspected commit. dotnet list OgmaLibrary.sln package --vulnerable --include-transitive reported no vulnerable package on 2026-08-13. Evidence: ../05-testing-documentation/test-completion-report.md.

- Hosted CI green on both platforms. .github/workflows/ci.yml is configured for Windows and macOS, but current hosted-run evidence was not inspected. Owner: engineering lead. Evidence: named green run at the release-candidate commit. Target: every release candidate.

## 6.3	3. Release-Engineering Readiness

- Packaging configuration exists. No Velopack/MSIX/DMG configuration is in the repository. Owner: Peter Bamuhigire. Evidence: packaging config + first Dev-channel artifact. Target: Phase 22.

- Code signing and notarization operational. No certificates provisioned; no signing step exists. Owner: Peter Bamuhigire (procurement). Evidence: signed Dev build from the pipeline; key-custody record. Target: Phase 22.

- Update trust chain verified. Design ratified (ADR-0009, CTRL-OGMA-012/013); tamper-rejection tests not possible until packaging exists. Owner: Peter Bamuhigire. Evidence: tampered-descriptor and tampered-package rejection tests green on both platforms. Target: Phase 22.

- Rollback drill executed. Never run (no feed exists). Owner: Peter Bamuhigire. Evidence: drill record incl. feed re-point + migration backup-restore. Target: Phase 22.

- Database migration backup-before-apply has automated evidence. Implemented and tested (Catalogue/MigrationTests.cs, 11 migrations). Release-candidate restore/rollback drill remains a separate unchecked gate.

- Change window and freeze policy communicated to testers. Policy written (deployment guide Section 5); no tester community exists yet. Owner: Peter Bamuhigire. Target: Phase 23.

## 6.4	4. Operations and Infrastructure Readiness

- Release host and channel feeds provisioned. No release host exists. Owner: Peter Bamuhigire. Evidence: Dev/Alpha/Beta/Stable feed paths serving a signed descriptor. Target: Phase 22.

- Opt-in telemetry verified. The application transmits no telemetry today (nothing is built — which trivially satisfies the privacy default but provides no health signal). The opt-in surface, minimized payload, and erasure path are Phase 23 scope. Owner: Peter Bamuhigire. Evidence: default-off verification test + payload schema review. Target: Phase 23.

- SLOs instrumented with error budgets. Definitions exist (monitoring-slo.md); no measurement surface exists. Owner: Peter Bamuhigire. Target: Phase 23.

- Runbook rehearsed. Procedures written (runbook.md) including the LAN-host operational runbook; the signing-key-compromise tabletop and malicious-update drill have not been run. Owner: Peter Bamuhigire. Evidence: drill records. Target: Phase 23.

- Security hardening pass complete. Phase 19 (threat model execution, SAST baseline, untrusted-PDF isolation hardening, at-rest encryption, classroom DPIA) not started. Owner: Peter Bamuhigire. Target: Phase 19.

- Accessibility and localization gates. WCAG 2.2 AA audit and es/it/de completion are Phase 21 scope; en + fr resources and pseudolocale tests exist today. Owner: Peter Bamuhigire. Target: Phase 21.

- Premium icon set procured. Placeholder icons in use; premium PNG procurement from the owner outstanding — release blocker by policy (_context/build-status.md). Owner: Peter Bamuhigire (as product owner). Target: before first Beta.

## 6.5	5. Decision Record

- Recommendation: NO-GO for public Beta. Conditions to revisit: Sections 2–4 items closed through the phase plan — Phase 19 (security) → Phase 20 (performance acceptance) → Phase 21 (a11y/i18n/E2E) → Phase 22 (packaging/signing/rollback) → Phase 23 (soak + drills + SLOs).

- Fastest credible path to Beta per the grand-plan estimates: 16 engineer-weeks of phase work (3+3+4+3+3) plus the ≥ 2-week soak.

- This register is updated in the same change as any phase exit; it must never disagree with Test Strategy Section 7.