# Risk Register

Table of Contents

# 1	Risk Register — Ogma Library

| Field | Value |
| --- | --- |
| Project | Ogma Library |
| Document | Risk Register |
| Owner | Chwezi Core Systems |
| Author | Peter Bamuhigire, Lead Consultant, Chwezi Core |
| Version | 2.1 |
| Date | 2026-08-13 |
| Standard basis | ISO 31000:2018; ISO/IEC 27001:2022 §6.1; IEEE 1012-2016 anomaly identification |
| Classification | Confidential — Internal Use Only |

Version 1.0 split risks across two formats (bulleted security risks, tabular delivery risks). Version 2.0 normalises all risks into one table, updates every status against the as-built evidence in _context/build-status.md and the codebase git history, and adds six risks (RISK-018 through RISK-023) arising from the classroom scope, the delivery model, and the open build items.

## 1.1	1. Scoring Method

- Likelihood (L) and Impact (I) each 1–5 (1 = Rare/Negligible, 3 = Possible/Moderate, 5 = Almost Certain/Catastrophic). Score = L × I.

- Tolerance: 1–4 Low, 5–9 Medium, 10–15 High, 16–25 Critical. Scores of 10+ require a named mitigation with a dated verification point.

- Status values: Open (mitigation pending), Mitigated — verification pending (controls implemented in code; adversarial or formal verification scheduled), Retired (risk event can no longer occur; evidence cited), Accepted (owner-recorded acceptance).

- Ratings shown are post-mitigation (residual). Owners are roles per _context/stakeholders.md.

## 1.2	2. Risk Register

| ID | Risk | L | I | Score | Mitigation → controls/decisions | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RISK-001 | Provider credential exposure via logs, settings, or crash reports | 2 | 4 | 8 | OS credential storage, log redaction, deletion on provider removal → CTRL-001, CTRL-002, CTRL-003 | Engineering lead | Mitigated — verification pending (Phase 19 SAST/review, US-051) |
| RISK-002 | Malicious/malformed PDF exploits render or OCR path | 3 | 4 | 12 | Untrusted-content workers, scripting disabled, bounded time/memory → CTRL-004..007 | Engineering lead | Mitigated — verification pending (malformed-corpus adversarial run, Phase 19) |
| RISK-003 | Metadata write-back corrupts an original file | 1 | 5 | 5 | Backup → diff → verify-reopen → restore inside validated root → CTRL-011, NFR-PROD-010; fault-injection tests pass | Engineering lead | Mitigated — verification pending (Phase 20 fault-injection re-run on reference hardware) |
| RISK-004 | Path traversal / symlink escape beyond library root | 1 | 4 | 4 | Canonicalise and validate all paths; quarantine traversal entries → CTRL-008..010; Phase 16 path-validation tests | Engineering lead | Mitigated — verification pending (Phase 19) |
| RISK-005 | Tampered or unsigned update installed | 2 | 4 | 8 | Code-signing, signature verification before install, authenticated update channel → CTRL-012, CTRL-013, ADR-0009 | Engineering lead (release) | Open (no packaging exists yet; lands with US-056, Sprint-4) |
| RISK-006 | User content transmitted off-device without intent | 1 | 5 | 5 | Single egress chokepoint, active-tier requirement, confirmed payload preview, minimisation → CTRL-016, CTRL-017, CTRL-020; architecture test forbids bypass | AI engineer | Mitigated — verification pending (Phase 19 review of gateway paths) |
| RISK-007 | AI history/embeddings retain content after expected deletion | 2 | 3 | 6 | Scoped erasure of history, vectors, cached responses; provider deletion path surfaced → CTRL-023, NFR-PROD-014; erasure-residue tests pass | AI engineer | Mitigated — verification pending |
| RISK-008 | Cross-jurisdiction transfer without notice or lawful basis | 3 | 4 | 12 | Provider region surfaced pre-use; DPIA screening per off-device feature → CTRL-021, CTRL-024; DPIA v2.0 | Product owner | Open (target-jurisdiction decision outstanding — audit finding F-14, DPIA §2.7) |
| RISK-009 | Provider trains on user content without distinct consent | 1 | 4 | 4 | No-training flag default opt-out; separate explicit opt-in → CTRL-022 | AI engineer | Mitigated — verification pending |
| RISK-010 | WebView-to-Three.js bridge unreliable on macOS WKWebView | 1 | 3 | 3 | Phase 01 spike + Phase 14 shipped typed bridge with ogma:// scheme → ADR-0003 | Engineering lead | Retired 2026-06-02 (3D shelf implemented and tested; evidence: OgmaLibrary.Bookshelf3D, Phase 14 commits) |
| RISK-011 | Chosen PDFium wrapper fails to package on a target platform | 1 | 3 | 3 | Wrapper benchmark spike; renderer isolated behind adapter → ADR-0004 | Engineering lead | Retired 2026-05-31 (PdfiumAdapter via PDFtoImage/SkiaSharp shipped; reader in production use in dev builds) |
| RISK-012 | 3D shelf degrades below frame-rate budget on large libraries | 3 | 2 | 6 | Virtualised shelf, visible-book cap, search-driven focus, grid/list fallback → NFR-OGMA-006 | Engineering lead | Mitigated — verification pending (binding measurement on UHD 620 at Phase 20, US-053) |
| RISK-013 | Full-text + embedding index grows unmanageably | 2 | 3 | 6 | Sidecar storage, configurable indexing, size exposed in Index Manager → FR-SEARCH-006, NFR-OGMA-004 | Engineering lead | Mitigated — verification pending (50,000-item scale test at Phase 20) |
| RISK-014 | External metadata providers return conflicting values | 3 | 1 | 3 | Field-level provenance and reviewable confidence merge; local edits win → FR-META-003, FR-META-004 | Engineering lead | Retired 2026-05-31 (merge policy + provenance implemented with provider-stub tests) |
| RISK-015 | OCR slow or inaccurate on scanned documents | 3 | 2 | 6 | Optional background OCR, stored confidence, OCR-derived labelling → FR-READ-010 | Engineering lead | Mitigated — verification pending (accuracy sampling on golden corpus at Phase 20) |
| RISK-016 | Runtime/package incompatibility with the .NET baseline | 1 | 3 | 3 | Phase 00 compatibility matrix; .NET 8 fallback only behind documented blocker → ADR-0001 | Engineering lead | Retired 2026-05-30 (net10.0 solution builds warnings-as-errors with full test suite; residual package-mix issue tracked separately as RISK-022) |
| RISK-017 | Extracted text out of reading order pollutes search/citations | 3 | 2 | 6 | Extraction-quality flags; extracted text never treated as clean for AI/citation → FR-SEARCH-002 | Engineering lead | Mitigated — verification pending (two-column corpus checks at Phase 20) |
| RISK-018 | LAN host mode opens an attack surface (TLS misconfiguration, enrollment abuse, streaming endpoint exploitation) on school networks | 3 | 4 | 12 | Off-by-default host, TLS + TOFU fingerprints, enrollment codes, per-profile auth, path validation, session revocation, host audit → FR-LAN-001..010, CTRL-016, CTRL-018; adversarial testing scheduled | Engineering lead | Open (Phase 19 threat-model execution, US-051, Sprint-1) |
| RISK-019 | Minors' reading and AI-query data mishandled in classroom deployments (surveillance, exposure, retention) | 3 | 5 | 15 | Aggregate-only disclosed dashboards → FR-CLIENT-012; metadata-only class default and admin-gated content tier → FR-ADMIN-006, FR-ADMIN-007; student deletion and institutional purge → FR-ADMIN-012, FR-ADMIN-013; DPIA v2.0 minors section (03-dpia/) | Product owner | Open (jurisdiction decision F-14 and school-controller guidance outstanding; controls implemented) |
| RISK-020 | Microsoft Store / Mac App Store submission rejected (sandbox, entitlement, or policy findings), delaying launch | 3 | 3 | 9 | Early submission in Sprint-4 with filing (not approval) as exit criterion; Velopack direct channel as fallback → ADR-0009 | Product owner | Open (Phase 22) |
| RISK-021 | Single-maintainer bus factor: the compressed Phases 00–18 build concentrated all system knowledge in one contributor | 4 | 4 | 16 | XML-doc'd code, ADR catalog (ADR-0001..0015), grand-plan phase READMEs, this documentation baseline; team-of-3 forward plan spreads ownership by role | Product owner | Open (Critical band; standing item at every sprint review until a second contributor closes a full story solo) |
| RISK-022 | Runtime/package incompatibility returns after a dependency change | 1 | 3 | 3 | Aligned .NET 10/EF Core 10 baseline; Release suite and vulnerability audit → ADR-0016 | Engineering lead | Retired for commit 26df983 on 2026-08-13; reopen on package/runtime change |
| RISK-023 | Premium icon procurement delay blocks the release gate (placeholders are a release blocker by policy) | 4 | 3 | 12 | Owner decision + asset delivery, or recorded waiver, before Sprint-4 packaging → retrospective action A-3; grand plan principle 8 | Product owner | Open (due 2026-08-21) |
| RISK-024 | Primary UI ships with the banned Inter dependency and placeholder styling, weakening readability, identity, and premium positioning | 4 | 3 | 12 | Implement the controlled Spectral/Public Sans/JetBrains Mono system, replace icon placeholders, and run keyboard/contrast/zoom/manual screen review | Design/UX lead | Open; blocks design acceptance and store screenshots |
| RISK-025 | Pricing, school-seat terms, update obligations, refunds, taxes, or AI cost policy are sold before commercial controls are ratified | 3 | 4 | 12 | Business-case assumptions register, finance quality gate, store gross-to-net reconciliation, revenue/tax policy, refund/chargeback process, AI quota/cost controls | Product owner + finance controller | Open; blocks paid launch and education contracting |

## 1.3	3. Residual-Risk Summary

- Critical band (16–25): RISK-021 only; no acceptance record was found, so it remains open.

- High band (10–15): RISK-002, RISK-008, RISK-018, RISK-019, RISK-023, RISK-024, and RISK-025.

- Retired with point-in-time evidence: RISK-010, RISK-011, RISK-014, RISK-016, and RISK-022. Retired risks remain visible and reopen when their trigger occurs.

## 1.4	4. Review Cadence and Escalation

- The register is reviewed at each sprint review (2-week cadence, starting 2026-07-24) and at every phase gate.

- A new risk takes the next sequential identifier; a retired risk keeps its row, closure date, and evidence pointer.

- Any risk entering the Critical band, and any High risk missing its dated verification point, escalates to the product owner at the sprint review; escalations and acceptances are recorded in the sign-off ledger.

- Trigger conditions for out-of-cycle reassessment: a Phase 19 adversarial finding, a store-submission rejection, any classroom-pilot incident involving student data, and any change to a baselined CTRL requirement (which also requires a Change Impact Analysis entry).